## Week
BRIGHTWATER REMODELING
Schedule — week of Oct 26, 2026
Job | Mon 10/26 | Tue 10/27 | Wed 10/28 | Thu 10/29 | Fri 10/30
1420 Johnson St | Brian, Luke | Brian, Luke | Brian / Luke / Helper | Brian, Luke | Brian
1240 Johnson St | Manny & Rosa | Manny & Rosa | Manny | TBD | Manny & Rosa
Whitfield addition | Kenji Trevor Ike | Kenji Trevor Ike | Kenji Trevor | Kenji Trevor Ike Mike R | Kenji Trevor
88 Larchmont Ave | Dom, Nate | Dom, Nate, Delta Electric LLC |  | Dom, Nate | open
Fenwick basement | Phil + Mike R | Phil + Mike R | Phil, Rosa, Mike R | Phil + Mike R | done
Riverside Dental TI | Mike B | Mike B, Delta Electric LLC | Mike B + Ike | Delta Electric LLC | Mike B, Nate
Shop |  |  | Dom | Luke | Ike, Trevor, Mike R
OFF |  | Kenji (dentist) |  |  | Luke
VAC |  |  |  | Rosa
Delta Electric LLC - rough-in inspection at Riverside Thu, someone has to let them in.
Rosa's vacation day is Thu 10/29. Dumpster at Fenwick gets pulled Fri.