## Materials
Item | Qty | For job | Supplier | Need by | Ordered by
2x10x16 SPF #2 | 48 | Lot 3 Sorrel Ridge | Hillman Lumber | 2026-10-13 | Dave
1/2" CDX ply | 60 | Lot 7 Sorrel Ridge | Hillman Lumber | 2026-10-14 | Raymond
LUS210 hangers | 2 boxes | Lot 3 Sorrel Ridge | Hillman Lumber | 2026-10-13 | Curtis
Base cabinets (12 pcs) | 1 | Kim remodel | Cabinet Depot | 2026-10-15 | Tobias
Composite decking 16' | 40 | Halvorsen deck | Coastal Supply | 2026-10-13 | Sam
1/2" drywall 4x12 | 30 | Kim remodel | Coastal Supply | 2026-10-16 | Nell
Joist tape | 3 | Halvorsen deck | Coastal Supply | 2026-10-13 | Sam
Ice & water shield | 6 | Mt. Olive Church roof | Northside to supply
Construction adhesive | 24 | Lot 7 Sorrel Ridge | Hillman Lumber | 2026-10-14 | Eddie
Call orders in by 2pm for next-day delivery.

## Schedule
ALDER CREEK HOMES — CREW SCHEDULE
Week of 10/12/2026
Job / Address | Mon 10/12 | Tue 10/13 | Wed 10/14 | Thu 10/15 | Fri 10/16
Lot 3 Sorrel Ridge | Dave, Curtis, Jamie | Dave, Curtis, Jamie | Dave, Curtis, Jamie | Dave, Curtis | Dave, Curtis, Jamie
Lot 7 Sorrel Ridge | Raymond, Eddie, Gordo | Raymond, Eddie, Gordo | Raymond, Eddie, Helper | Raymond, Eddie, Gordo | Raymond, Eddie
Kim remodel | Tobias, Lucas | Tobias, Lucas | Tobias, Nell | Tobias, Nell | TBD
Halvorsen deck | — | Sam, Nell | Sam, Gordo | Sam | Sam, Nell
Mt. Olive Church roof | Northside Roofing LLC | Northside Roofing LLC |  | Northside Roofing LLC | done
Shop | Nell |  | Lucas | Lucas | Gordo
OFF |  |  |  | Jamie | Tobias, Lucas
Lot 3 walk-through with the buyers Thu 4pm.